Transportation Infrastructure Precast Innovation Center

(TRANS-IPIC)

University Transportation Center (UTC)

Digital Twins for Evaluation of Precast Concrete Bridge Girders

UB-25-RP-01

Quarterly Progress Report

For the performance period ending March 31, 2026

Submitted by:

Pinar Okumus, Associate Professor, pinaroku@buffalo.edu

Department of Civil, Structural and Environmental Engineering

University at Buffalo, the State University of New York

Collaborators / Partners:

None

Submitted to:

TRANS-IPIC UTC

University of Illinois Urbana-Champaign

Urbana, IL

TRANS-IPIC Quarterly Progress Report:

Project Description:

- Research Plan - Statement of Problem

Bridge owners need smart tools to manage their aging inventories within budget and safety constraints. This project is developing a digital twin (DT) framework tailored for prestressed concrete bridges that can be used for continuous condition assessment through integrated inspection, evaluation, and analysis. A DT is a dynamic virtual representation of a bridge that evolves with time by incorporating data from design, construction, inspection, monitoring, evaluation, and structural analysis. The proposed DT incorporates a bridge evaluation tool that estimates stiffness changes in girders during service life and finite element models that can determine the impact of stiffness change on load distribution. This can capture beneficial load re-distribution effects stemming from stiffness changes to eliminate unduly conservative load ratings and bridge girder health assessments. This work can lay the foundation for data-informed infrastructure management, demonstrating how DTs enhanced with machine learning can transform bridge health monitoring from reactive to proactive.

- Research Plan - Summary of Project Activities (Tasks)

Task 1. Identify a bridge: In this task, a real bridge that has prestressed girders and a concrete deck will be identified in collaboration with a State Department of Transportation. Information related to the bridge such as bridge plans, maintenance history, field instrumentation data, and inspection reports will be collected.

Task 2. Create a digital twin workflow: A workflow will be created to lay out the DT components and to ensure continuous data transfer between components. The components include crack width sensing, a machine learning algorithm that detects stiffness changes, and system and member level finite element analysis (FEA) to determine load distribution and capacity, respectively.

Task 3. Evaluate girder stiffness: In this task, girder stiffness at given crack widths will be estimated using an existing machine learning algorithm developed by the investigators. The change in stiffness will be used as an input for task 4.

Task 4. Incorporate load redistribution into analyses: In this task, the stiffness predictions from task 3 will be used to update a system-level FEA of the testbed bridge. This analysis will determine how stiffness degradation in one or more girders alters load distribution across the bridge superstructure.

Task 5. Evaluate girder capacity: A member-level FEA will be performed for individual prestressed girders, considering the stiffness change identified in task 3, to estimate their residual capacity.

Task 6. Compare capacity to demand: The capacity obtained in Task 5 will be compared to the demand that captures load re-distribution obtained in Task 4. This will allow generating guidance on whether the bridge is safe, it should be load posted or closed to traffic.

Project Progress:

- Progress for each research task

Task 1. Identify a bridge [10% completed to date]: The LTBP InfoBridge (Federal Highway Administration, N/A) database published by the Federal Highway Administration is being scanned to identify a suitable prestressed concrete bridge in New York State near Buffalo, NY. When candidate bridges are identified, the State Department of Transportation (DOT) will be contacted for information on a bridge with preferably a known performance problem. An additional DOT was contacted to request a prestressed concrete bridge with a known performance problem, but a bridge was not immediately available.

Task 2. Create a digital twin workflow [0% completed to date]: This task has not started.

Task 3. Evaluate girder stiffness [5% completed to date]: A method for predicting the stiffness of the selected bridge is available. Progress on this task depends on completion of task 1.

Task 4. Incorporate load redistribution into analyses [0% completed to date]: This task has not started.

Task 5. Evaluate girder capacity [0% completed to date]: This task has not started.

Task 6. Compare capacity to demand [0% completed to date]: This task has not started.

- Percent of research project completed

This project is 5% completed.

- Expected progress for next quarter

In the next quarter, Tasks 1 will be completed and Task 3 will be initiated.

- Educational outreach and workforce development

None.

- Technology Transfer

None.

Research Contribution:

- Papers that include TRANS-IPIC UTC in the acknowledgments section:

None.

- Presentations and Posters of TRANS-IPIC funded research:

None.

- Please list any other events or activities that highlights the work of TRANS-IPIC occurring at your university (please include any pictures or figures you may have). Similarly, please list any references to TRANS-IPIC in the news or interviews from your research.

None.

Appendix 1: Research Activities, leadership, and awards (cumulative, since the start of the project)

- Number of presentations at academic and industry conferences and workshops of UTC findings

- No. = 0

- Number of peer-reviewed publications submitted based on outcomes of UTC funded projects

- No. = 0

- Number of peer-reviewed journal articles published by faculty.

- No. = 5

- Number of peer-reviewed conference papers published by faculty.

- No. = 0

- Number of TRANS-IPIC sponsored thesis or dissertations at the MS and PhD levels.

- No. MS thesis = 0

- No.  PhD dissertations = 0

- No. citations of each of the above = 0

- Number of research tools (lab equipment, models, software, test processes, etc.) developed as part of TRANS-IPIC sponsored research.

- None

- Number of transportation-related professional and service organization committees that TRANS-IPIC faculty researchers participate in or lead.

- Professional societies

  - No. participated in = 5

  - No. lead = 0

- Advisory committees (No. participated in & No. led)

  - No. participated in = 0

  - No. lead = 0

- Conference Organizing Committees (No. participated in & No. led)

  - No. participated in = 2

  - No. lead = 0

- Editorial board of journals (No. participated in & No. led)

  - No. participated in = 5

  - No. lead = 2

- TRB committees (No. participated in & No. led)

  - No. participated in = 1

  - No. lead = 0

- Number of relevant awards received during the grant year

- No. awards received = 1

- Number of transportation related classes developed or modified as a result of TRANS-IPIC funding.

- No. Undergraduate = 0

- No. Graduate = 2

- Number of internships and full-time positions secured in the industry and government during the grant year.

- No. of internships = 0

- No. of full-time positions = 0

References:

Federal Highway Administration (N/A). LTBP InfoBridge, retrieved: March 2026, available at https://infobridge.fhwa.dot.gov/